## Est Guidelines
VERSION HISTORY
|  |  | Ver. No | Date of Release | Prepared By | Reviewed / Approved By | List of changes from Previous Version
| Project Estimation Sheet |  | 1.0 | 2026-02-17 | Jannatul Ferdous Lamia | Tahmina Khatoon
| Version 1.0 |  | Notes
Document Number: BS23-EST-2.0
QMS Document Version Reference: BS23-QMS-2.0
QMS Document Reference: 2.0
Definitions, Acronyms, and Terminology
Complexity Category | Complexity Definition (TBC by Project Team) | Dev Unit Prodcutivity (Man Days) (TBC by Project Team) | Item |  | Dexcription / Expansion
O | Zero | 0
XXS | XX Small | 1
XS | Extra Small | 2 | Dev |  | Development
S | Small | 4 | PM |  | Project Management
M | Medium | 8 | QA |  | Quality Assurance
L | Large | 12 | LC |  | Life Cycle
XL | Extra Large | 24 | CM |  | Configuration Management
|  |  | UI |  | User Interface
|  |  | SMD |  | Standard Man Days
Terminology | Process Includes are… | Effort Category
Construction Effort | Coding and Unit Testing | Dev
Project Management Effort | Planning, Estimating, Review, Control, Team Meeting, Reporting and Closing activities | PM
Quality Management Effort | Review of Project Artifact such as Plans, Technical Docuemnts (Requirement Specification, System Design,…) | QA
Requirement Analysis Effort | Collect Requirement, Define Scope, Prepare Requirement Specification, Test Plan | LC
System Design Effort | Project Structure, System Design (Design Standard, Database diagram, Class diagram, Common methodology, UI Design, Unit Specification. Test Plan) | LC
System Testing Effort | Writing Test Cases, Functional and Integration testing, Reporting Bug, Regression Testing etc | LC
Implementation Effort | Prepare Product User Documents, Internal and External Release to either Stage or Live Server | LC
Configuration management Effort | Ensuring all artifacts related to project are under configuration control | CM
Effort Category | Additional Overhead effort with respect to Dev effort
LC | 0%
PM | 10%
QA | 12%
CM | 0%
DS | 0%
USD
Per ManDays Rate | 200

## Total Estimation
Ap | Feature | Total Cost (USD) | Mandays
1 | Branded Mobile Application development with default features | 1800 | 9 | Sl. | Description | Amount (USD)
| Admin Panel | 3800 | 19
| Total = | 5600 | 28 | 1 | Project initiation (upon signing) | 3000
|  |  |  | 2 | Milestone 1 (Core Learning & User Management) | 3560
|  |  |  | 3 | Milestone 2 (Assessment, Reporting & Communication) | 3560

## WBS
WBS ID | Module | Feature | Description | Comments | Tshirt Size | Man Days | Milestone | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5
A 1.1 | Idea Managemnet | Idea Submission System | Allows employees, customers, and partners to submit innovation ideas through structured digital forms with customizable fields. |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 1.2 |  | Workflow Automation | Automated routing of ideas through predefined approval stages (review, evaluation, approval, rejection, implementation). |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 1.3 |  | Idea Catagorization & Tagging | Organize ideas by department, business unit, theme, priority level, or innovation category. |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 1.4 |  | Voting & Commenting System | Users can vote, like, and comment on ideas to encourage engagement and collaborative improvement. |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 1.5 |  | Confidential Idea Archieve | Secure storage of submitted ideas with restricted access and long-term archival capability. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 2.1 | Campaign & Challenge Management | Campaign Creation | Admin can create innovation campaigns aligned with strategic goals. |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 2.2 |  | Campaign Workflow Configuration | Customizable workflows for each campaign (submission deadline, review stage, scoring, approval). |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 2.3 |  | Campaign Monitoring Dashboard | Real-time tracking of campaign participation, submissions, and progress. |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 2.4 |  | Campaign Closure & Reporting | Real-time tracking of campaign participation, submissions, and progress. |  | O | 0 |  | 0 | 0 | 0 | 0 | 0
A 3.1 | Evaluation & Governance | Custom Scoring Framework | Allows administrators or evaluators to define and customize the scoring standards used to assess ideas, projects, or proposals. |  | O | 1 |  | 0 | 0 | 0 | 0 | 0
A 3.2 |  | Evaluation Panels | Assign expert reviewers or evaluation committees for structured idea assessment. |  | O | 2 |  | 0 | 0 | 0 | 0 | 0
A 3.3 |  | Stage-Gate Approval Process | Multi-stage workflow ensures transparency, accountability, and better decision-making throughout the entire process. |  | O | 4 |  | 0 | 0 | 0 | 0 | 0
A 3.4 |  | Governance Control & Audit | Complete tracking of evaluation decisions, reviewer comments, and approval history. |  | O | 2 |  | 0 | 0 | 0 | 0 | 0
A 4.1 | Collaboration & Co-Creation | Discussion Boards | Provides a structured online discussion space where users can share ideas, give feedback, and improve proposals through organized conversations. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 4.2 |  | Team Collaboration Spaces | Dedicated digital workspace for innovation teams to co-develop selected ideas. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 4.3 |  | Tagging & Mentions | Users can tag colleagues or subject matter experts in posts, assignments, or discussions to invite their input, feedback, or clarification. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 4.4 |  | E-mail & Notification | The system will send automated notifications by integrating with email services using SMTP AUTH or Microsoft Graph API (OAuth 2.0). |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 5.1 | Analytics & KPI Dashboard | Participation Analytics | Track user engagement, submissions per department, and campaign activity. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 5.2 |  | Innovation Funnel Dashboards | Provides a visual workflow that tracks ideas through each stage of the review process (Submitted → Reviewed → Approved → Implemented). |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 5.3 |  | ROI & Impact Tracking | Measure financial and operational impact of implemented ideas. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 5.4 |  | Leadership KPI Reports | Custom dashboards aligned with the organization’s innovation framework. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 6.1 | Integration & API | Microsoft Teams Integration | Allow users to share ideas, get notified instantly, and collaborate in real-time inside MS Teams without switching platforms. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 6.2 |  | SharePoint Integration | Allow users to share ideas, get notified instantly, and collaborate in real-time inside MS Teams without switching platforms. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 6.3 |  | Power BI Integration | Advanced analytics and reporting visualization that collects, processes, analyzes, and presents data. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 6.4 |  | HR & Internal System | System that connects and synchronizes HR and internal tools, and project data to stay accurate and up-to-date across platforms. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 6.5 |  | Rest API Framework | Secure APIs for data exchange with internal and external applications. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 7.1 | Localization | Bilingual Interface (Arabic/English) | Allowing users to seamlessly switch between Arabic (automatically switches right-to-left layout) and English. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 7.2 |  | Laws & Regulations | Comply with all local laws and regulations in the UAE, including data protection, privacy, and digital governance standards. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 8.1 | System & Cloud Setup | Cloud Hosting Environment | Provide a secure and reliable cloud-based setup for your system, using enterprise-level servers. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 8.2 |  | Backup & Disaster Recovery | Implemented an automated system that regularly saves copies of your data and files. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 9.1 | Implementation & Support | Platform Setup & Configuration | Ensure all integrations with existing tools (like email, analytics, or storage) are properly set up. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 9.2 |  | Data Migration | Safely transfer all existing ideas, innovation records, and related data from legacy systems. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 9.3 |  | Admin & User Training | Offer training on managing the platform, creating reports, and using advanced features. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 9.4 |  | Annual Support & Maintainance | Deliver regular software updates, including new features and security patches. |  | O |  |  | 0 | 0 | 0 | 0 | 0
A 10.1 | AI Features | Idea Enhancer | Automatically improves and polishes the wording of submitted ideas to make them clearer, more professional, and easier.
A 10.2 |  | Tag Suggestion | Analyzes the idea content and automatically recommends relevant categories and tags, helping users properly classify their ideas and improving searchability.
A 10.3 |  | Duplicate Check | Scans the database to detect similar or duplicate ideas and alerts before submission and improving review efficiency.
A 10.4 |  | Idea Summary | Generates a short, clear summary of each submitted idea so reviewers and decision-makers can quickly understand the key concept without reading the full description.
A 10.5 |  | Description Generator | Assists administrators in automatically drafting campaign or challenge descriptions, objectives, and guidelines based on minimal input, saving time and ensuring consistency.
A 10.6 |  | Close Summary | Automatically produces end-of-campaign reports that summarize participation levels, key outcomes, top ideas, and overall performance metrics.
A 11.1 | Elastic Search | Search | Implements high-speed search and indexing capabilities to enable fast idea lookup, also accurate duplicate detection across large volumes of data.
[6 empty] | 9 |  | 0 | 0 | 0 | 0 | 0

## Admin Panel (hidden)
WBS ID | Module | Feature | Description | Comments | Tshirt Size | Man Days | Milestone | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5
B 1.1 | Platform Admin | Authentication & Login | Login to the app using platform credentials; access restricted to Admin role. |  | XXS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1
B 1.2 |  | Role-Based Access Control | Define and assign roles for schools, managers, teachers, and students; control which features each role can access. |  | XS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2
B 1.3 |  | School Creation & Management | Create new schools, assign school managers, and configure school-level environments. |  | XS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2
B 1.4 |  | Global Analytics | View metrics across all schools, including user activity, course completion, and engagement. (number of users, number of courses, course wise completion) |  | XS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2
B 2.1 | School Manager | Authentication & Login | Login with school-level credentials; access restricted to the manager’s school. |  | XXS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1
B 2.2 |  | User Management | Add teachers, manage teacher roles, and oversee student registrations for the school. |  | XS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 1
B 2.3 |  | Enrollment & Course Management | Assign students and teachers to courses; manage schedules and course availability within the school. |  | XS | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1
B 2.4 |  | School-Level Dashboard | View performance reports and course progress for all students and teachers in their school. |  | XS | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1
B 2.5 |  | Activity Logs | Track actions and updates by teachers and students in their school environment. |  | XXS | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 1
B 3.1 | Platform & System Management | Profile Management | View and update profile details (name, email, profile picture) synced with Moodle backend. |  | XXS | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 1
B 3.2 |  | Multilingual Interface | Access the app in supported languages (English, Arabic) based on user selection. |  | XXS | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 1
B 3.3 |  | Secure API Integration | All app interactions communicate securely with Moodle backend using token-based authentication. |  | XXS | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 1
B 3.4 |  | Branding | App displays Learnerbit logo, colors, and splash screen consistently across iOS and Android. |  | XXS | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 1
[5 empty] | O | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 19 |  | 10 | 9 | 0 | 0 | 0

## Sprint Planning (hidden)
WBS ID | Module | Feature | Description | Sprint | Tshirt Size | Man Days
B 1.1 | Platform Admin | Authentication & Login | Login to the app using platform credentials; access restricted to Admin role. | Sprint 1 | XXS | 1
B 1.2 | Platform Admin | Role-Based Access Control | Define and assign roles for schools, managers, teachers, and students; control which features each role can access. | Sprint 1 | XS | 2
B 1.3 | Platform Admin | School Creation & Management | Create new schools, assign school managers, and configure school-level environments. | Sprint 2 | XS | 2
B 1.4 | Platform Admin | Global Analytics | View metrics across all schools, including user activity, course completion, and engagement. | Sprint 1 | XS | 2
B 2.1 | School Manager | Authentication & Login | Login with school-level credentials; access restricted to the manager’s school. | Sprint 1 | XXS | 1
B 2.2 | School Manager | User Management | Add teachers, manage teacher roles, and oversee student registrations for the school. | Sprint 1 | XS | 2
B 2.3 | School Manager | Enrollment & Course Management | Assign students and teachers to courses; manage schedules and course availability within the school. | Sprint 2 | XS | 2
B 2.4 | School Manager | School-Level Dashboard | View performance reports and course progress for all students and teachers in their school. | Sprint 2 | XS | 2
B 2.5 | School Manager | Activity Logs | Track actions and updates by teachers and students in their school environment. | Sprint 2 | XXS | 1
B 2.6 | School Manager | Curriculum Management | Upload, update, or remove course content centrally; all changes propagate to all schools. | Sprint 2 | XS | 2
B 3.1 | Platform & System Management | Profile Management | View and update profile details (name, email, profile picture) synced with Moodle backend. | Sprint 2 | XXS | 1
B 3.2 | Platform & System Management | Multilingual Interface | Access the app in supported languages (English, Arabic) based on user selection. | Sprint 4 | XXS | 1
B 3.3 | Platform & System Management | Secure API Integration | All app interactions communicate securely with Moodle backend using token-based authentication. | Sprint 3 | XXS | 1
B 3.4 | Platform & System Management | Branding | App displays Learnerbit logo, colors, and splash screen consistently across iOS and Android. | Sprint 3 | XXS | 1
A 1.1 | Teacher | Authentication & Login | Login with teacher credentials; access limited to their assigned courses and students. | Sprint 1 | XXS | 1
A 1.2 | Teacher | Class & Student Management | View assigned courses and course content. | Sprint 3 | XXS | 1
A 1.3 | Teacher | Course Navigation & Content | Access course content, resources, and activities assigned to their classes; view content as students would. | Sprint 3 | XS | 2
A 1.4 | Teacher | Progress Tracking | Monitor individual student progress, grades, and quiz/assignment completion. | Sprint 4 | XS | 2
A 1.5 | Teacher | Activity Logs | Track their own and student activity within assigned courses. | Sprint 3 | XS | 2
A 1.6 | Teacher | Messaging & Announcements | Send messages and post announcements to students in their classes. | Sprint 4 | XXS | 1
A 2.1 | Student | Authentication & Login | Login with student credentials; access limited to assigned courses only. | Sprint 1 | XS | 2
A 2.2 | Student | Course Access & Navigation | View enrolled courses, navigate sections, topics, and activities within assigned courses. | Sprint 3 | XXS | 1
A 2.3 | Student | Content Viewing | Access and interact with SCORM packages, H5P activities, Moodle Books, Pages, and media files. | Sprint 3 | XS | 2
A 2.4 | Student | Quiz & Assignment Participation | Attempt quizzes and submit assignments; quizzes include randomization and timed submission. | Sprint 3 | S | 4
A 2.5 | Student | Grades & Feedback | View grades, teacher feedback, and assignment scores. | Sprint 4 | XS | 2
A 2.6 | Student | Certificates | View and download course completion certificates in PDF format. | Sprint 4 | XXS | 1
A 2.7 | Student | Messaging & Forum | Send messages to teachers and peers; participate in course discussion forums. | Sprint 4 | XXS | 1
A 2.8 | Student | Calendar & Notifications | Receive push notifications for events, deadlines, and announcements; view course calendar. | Sprint 4 | XS | 2
[5 empty] | O | 0
45
[7 empty] | Sprint 1 | 11
[7 empty] | Sprint 2 | 8
[7 empty] | Sprint 3 | 14
Sprint 1 | [6 empty] | Sprint 4 | 10
WBS ID | Module | Feature | Description | Sprint
B 1.1 | Platform Admin | Authentication & Login | Login to the app using platform credentials; access restricted to Admin role. | Sprint 1
B 1.2 |  | Role-Based Access Control | Define and assign roles for schools, managers, teachers, and students; control which features each role can access. | Sprint 1
B 1.4 |  | Global Analytics | View metrics across all schools, including user activity, course completion, and engagement. (number of users, number of courses, course wise completion) | Sprint 1
B 2.1 | School Manager | Authentication & Login | Login with school-level credentials; access restricted to the manager’s school. | Sprint 1
B 2.2 |  | User Management | Add teachers, manage teacher roles, and oversee student registrations for the school. | Sprint 1
A 1.1 | Teacher | Authentication & Login | Login with teacher credentials; access limited to their assigned courses and students. | Sprint 1
A 2.1 | Student | Authentication & Login | Login with student credentials; access limited to assigned courses only. | Sprint 1 | Sprint 1 | 11
B 3.4 | Platform & System Management | Branding | App displays Learnerbit logo, colors, and splash screen consistently across iOS and Android. | Sprint 3 | done in sprint 1 | 12
Sprint 2
WBS ID | Module | Feature | Description | Sprint
B 1.3 | Platform Admin | School Creation & Management | Create new schools, assign school managers, and configure school-level environments. | Sprint 2
B 2.3 | School Manager | Enrollment & Course Management | Assign students and teachers to courses; manage schedules and course availability within the school. | Sprint 2
B 2.4 |  | School-Level Dashboard | View performance reports and course progress for all students and teachers in their school. | Sprint 2
B 2.5 |  | Activity Logs | Track actions and updates by teachers and students in their school environment. | Sprint 2
B 3.1 | Platform & System Management | Profile Management | View and update profile details (name, email, profile picture) synced with Moodle backend. | Sprint 2 | Sprint 2 | 8
A 1.2 | Teacher | Class & Student Management | View assigned courses and course content. | Sprint 3 | moved to sprint 2
A 1.3 |  | Course Navigation & Content | Access course content, resources, and activities assigned to their classes; view content as students would. | Sprint 3 | moved to sprint 2
A 2.2 | Student | Course Access & Navigation | View enrolled courses, navigate sections, topics, and activities within assigned courses. | Sprint 3 | moved to sprint 2 | 12
Sprint 3
WBS ID | Module | Feature | Description | Sprint
B 3.3 | Platform & System Management | Secure API Integration | All app interactions communicate securely with Moodle backend using token-based authentication. | Sprint 3
A 1.4 | Teacher | Progress Tracking | Monitor individual student progress, grades, and quiz/assignment completion. | Sprint 4
A 1.5 |  | Activity Logs | Track their own and student activity within assigned courses. | Sprint 3
A 2.3 | Student | Content Viewing | Access and interact with SCORM packages, H5P activities, Moodle Books, Pages, and media files. | Sprint 3
A 2.4 |  | Quiz & Assignment Participation | Attempt quizzes and submit assignments; quizzes include randomization and timed submission. | Sprint 3 | Sprint 3 | 14
A 2.5 |  | Grades & Feedback | View grades, teacher feedback, and assignment scores. | Sprint 4
A 2.6 |  | Certificates | View and download course completion certificates in PDF format. | Sprint 4
Sprint 4
WBS ID | Module | Feature | Description | Sprint
B 3.2 | Platform & System Management | Multilingual Interface | Access the app in supported languages (English, Arabic) based on user selection. | Sprint 4
A 1.6 |  | Messaging & Announcements | Send messages and post announcements to students in their classes. | Sprint 4
A 2.7 |  | Messaging & Forum | Send messages to teachers and peers; participate in course discussion forums. | Sprint 4
A 2.8 |  | Calendar & Notifications | Receive push notifications for events, deadlines, and announcements; view course calendar. | Sprint 4 | Sprint 4 | 10
B 3.5 |  | Start and End date for school | While creating school platform admin will be able add expiry date for a particular school. School manager will see the expiry date in this dashboard. Before the expiration both platform admin and school admin will receive reminders for two times. Once expired Platform admin can pause the school instance from admin panel and delete the school from console if needed. | Sprint 4
B2.3.1 | School Manager | Enrollment through CSV | School manager will be able to upload CSV file containing student name, email, grade and section. After that students of a particular section will be assigned to section courses in bulk via Cohort feature in moodle. This permission will be given to school manager only. | Sprint 4

## Timeline
Milestone | W 1 | W 2 | W 3 | W 4 | W 5 | W 6 | W 7 | W 8 | W 9 | W 10 | W 11 | W 12 | W 15 | W 16 | W 17 | W 18 | W 19 | W 20 |  | Man days
1. Core Learning & User Management | [18 empty] | Milestone 1 | 0 | bar: W 1
2. Assessment, Reporting & Communication | [18 empty] | Milestone 2 | 0 | bar: W 5
3. Free Maintenance & Support | [18 empty] | Milestone 4 | 0 | bar: W 9
[19 empty] | total= | 0
Phase 1: Core Modules, Phase 2: Assessment & Reports, Phase 3: Communication & Deployment) for planning and costing?

## Exec view (hidden)
|  | Milestone 1 (Completed) |  |  |  | Milestone 2 (In progress) |  |  |  | Deployment
Sprint | Deliverable | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W7 | W8
Sprint 1 (1 Dec - 12 Dec'25) | Admin, Manager, Teacher, Student login; RBAC, user management | Milestone 1 (Completed) W1: Completed (12 dec'25)
Sprint 2 (15 Dec - 29 Dec'25) | School creation, enrollment, dashboards, Activity logs, profile management | Milestone 1 (Completed) W3: Completed (29 Dec'25)
Sprint 3 (01 Jan - 13 Jan'26) | Course access, navigation, secure API, Content viewing, quizzes, assignments, Certificates | Milestone 2 (In progress) W5: In Review (13 Jan'26)
Sprint 4 (14 Jan - 28 Jan'26) | Messaging, forum, calendar, notifications, multilingual, UAT support | Milestone 2 (In progress) W7: In Progress (28 Jan'26)
Deployment (by Feb 10, 2026) | Final deployment in Play store and app store | Deployment W7: To Do (10 Feb'26)